Sprint Backlog

Planeta — Sprint 1

Sprint Duration: 2 Weeks     |     17 March 2026 – 30 March 2026

Sprint Goal: Establish the foundational 'Planeta' infrastructure by implementing the layered architecture to enable secure user registration and login, while ensuring the daily survey engine functions with real-time scoring and Firestore persistence.

| Story | Task |  | Assignee | Estimation(hours) |  | Status |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Revise Design Document |  | Update UML Diagrams | Tenay Giray |  | 2.0 h |  | Done |
|  |  | Update the design pattern and architectural decisions | Tenay Giray |  | 1.0h |  | Done |
| Update Requirements Document as we have decided for Planeta to be a web application instead of a mobile application |  | Change the non-functional requirements related to this decision | Tenay Giray |  | 0.5h |  | Done |
| Complete QA Plan |  | Create Test Plan | İpek Atak |  | 2.0 h |  | Done |
|  |  | Quality Assurance Strategy | Nehir Adak |  | 1.0h |  | Done |
|  |  | Quality Factor and Metrics | Nehir Adak |  | 2.0h |  | Done |
| Complete user registration feature (PBI-01) |  | Design the register screen UI | Tenay Giray |  | 2.0h |  | In progress |
|  |  | Implement email and password validation logic | Tenay Giray |  | 2.0h |  | In progress |
|  |  | Implement unique username check | Tenay Giray |  | 1.0h |  | In progress |
|  |  | Handle authentication success/error states | Tenay Giray |  | 1.5h |  | In progress |
|  |  | Implement Firebase Auth Integration | Tenay Giray |  | 2.0h |  | In progress |
|  |  | Implement MockAuthService to simulate various register scenarios | Defne Saracel |  | 1.0h |  | In progress |
|  |  | Unit test for Email/Password Regex: Validate input formats before calling the Auth service. | Nehir Adak |  | 1.0h |  | In progress |
|  |  | Integration test: Verify user profile document creation in Firestore | İpek Atak |  | 1.0h |  | In progress |
| Complete login screen with authentication logic (PBI-02) |  | Design login screen UI | Tenay Giray |  | 2.0h |  | In progress |
|  |  | Implement authentication logic | Tenay Giray |  | 3.0h |  | In progress |
|  |  | Ensure authentication completes within 5 seconds | Tenay Giray |  | 2.0h |  | In progress |
|  |  | Handle authentication success/error states | Tenay Giray |  | 1.0h |  | In progress |
|  |  | Implement Firebase Auth Integration | Tenay Giray |  | 2.0h |  | In progress |
|  |  | Bug Fix: Resolve MultiProvider initialization and provider access bug | Tenay Giray |  | 1.0h |  | Done |
|  |  | Implement unit tests for email and password validation logic | İpek Atak |  | 1.0h |  | In progress |
|  |  | Implement MockAuthService to simulate various login scenarios | Tenay Giray |  | 1.0h |  | In progress |
| Complete logout feature(PBI-03) |  | Implement session termination | Tenay Giray |  | 2.0h |  | In progress |
|  |  | Handle post logout navigation | Tenay Giray |  | 1.0h |  | In progress |
| Build Survey Data Architecture and Firebase Integration |  | Create SurveyModel class fileds: id, timestamp, answers,score and feedback | İpek Atak |  | 1.5h |  | In progress |
|  |  | Implement toMap()/fromMap() for FireStore compatibility | İpek Atak |  | 2.5h |  | In progress |
|  |  | Unit test for Scoring Logic | Defne Saracel |  | 0.5h |  | To do |
|  |  | Integration test: Verify that survey answers are correctly mapped to the Firestore /surveys collection | Nehir Adak |  | 1.0h |  | To do |
| Implement Survey Service and Scoring Logic (PBI-05, PBI-06) |  | Implement ISurveyService interface | İpek Atak |  | 2.0h |  | In progress |
|  |  | Implement score calculation | İpek Atak |  | 1.0h |  | In progress |
|  |  | Implement feedback logic | İpek Atak |  | 1.0h |  | To do |
|  |  | Persist submitted survey entry to Firestore under /users/{uid}/surveys/ | İpek Atak |  | 1.0h |  | To do |
|  |  | Unit Test: Validate SurveyEntry Serialization | Nehir Adak |  | 0.5h |  | To do |
|  |  | Unit test: Test the hybrid scoring algorithm by ScoreCalculator.calculateScore() | Tenay Giray |  | 0.5h |  | To do |
| Complete survey screen |  | Design survey questions layout | Defne Saracel |  | 2.0h |  | In progress |
|  |  | Implement answer button widgets with grading scale | Defne Saracel |  | 2.0h |  | In progress |
|  |  | Build submit survey button and post-submission result view | Defne Saracel |  | 1.0h |  | In progress |
|  |  | Manage local survey state with SurveyProvider | Defne Saracel |  | 2.0h |  | In progress |
|  |  | Add validation for unanswered questions | Defne Saracel |  | 1.0h |  | In progress |
|  |  | Enforce one-survey-per-day lock | Defne Saracel |  | 1.0h |  | To do |
|  |  | Verify the internal state management and navigation flow of the SurveyScreen during user interaction | İpek Atak |  | 1.0h |  | To do |
|  |  | Use a MockSurveyService to verify that clicking "Submit" triggers notifyListeners(), transitions the UI from surveyNotSubmitted to surveySubmitted, and navigates the user back home | Nehir Adak |  | 1.0h |  | To do |
| Complete home screen |  | Set up main.dart | Nehir Adak |  | 3.0h |  | In progress |
|  |  | Design home screen UI | Nehir Adak |  | 2.0h |  | In progress |
|  |  | Implement navigation to daily survey and history screens | Nehir Adak |  | 1.5h |  | In progress |
| View user history with past survey scores and dates (PBI-07) |  | Design history screen UI listing all past survey entries | Nehir Adak |  | 3.0h |  | In progress |
|  |  | Display date and score for each entry by descending dates | Nehir Adak |  | 1.0h |  | In progress |
|  |  | Show empty state when no survey is completed | Nehir Adak |  | 1.0h |  | In progress |
|  |  | Implement loadHistory() in SurveyProvider (fetch from Firestore) | Nehir Adak |  | 1.0h |  | To do |
|  |  | Integration test: Mock data fetch to verify the list displays past dates and scores correctly | İpek Atak |  | 1.0h |  | To do |